## Sheet1
CIP-70QPT |  |  |  | Test No | Gray: Done /Red: Existing issues and additional inspection items /Yellow: Continuous confirmation
Level 1 | Level 2 | Level 3 | Level 4
Startup settings | etc |  |  | 1 | Symptom: If there is no input during startup settings, it enters power saving mode, but the home screen is displayed. Request: Needs modification to not apply power saving mode during startup settings, or to maintain the current screen without moving to the home screen even if applied.
| Startup settings guide |  |  | 2 | Symptom: When skipped, the entire startup setup procedure is skipped and the home screen does not move to . Request: Apply after modifying the UI in COMMAX.
| Language settings |  |  | 3 | 1. Request: Place English at the top See figma link:https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0/CIP-70QPT?type=design&node-id=4613-25255&mode=dev2. Request: Change from “Korean” to “Korean” (refer to COMMAX UI)
| Operation network |  |  | 4 | 1. Request: Change the security record to phone number format instead of IP. ->Change has been applied, but input is requested to be limited to 11 characters (20230919_142502.mp4)2.Request: The color of the keypad buttons is different from the GUI guide (common to the keypad). Refer to the figma link:https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25242&mode=design#559628336 3. Request: The building code is based on 4 digits, but can be applied in the same format no matter what value is entered. Example) 0001 input = 1 building, 001 input = 1 building, 1 input = 1 building (20230908_154452.mp4) 4. Building number Value cannot be stored (memory). It can be saved even if you go to the next or previous screen and then come back to the operation network screen (20230908_154452.mp4) 5. The default value of the operation server is 10.0.0.2 (default value) 6. For IP, check the valid format value and make sure the correct format is in place. If not, the text displayed in the instant message is: ‘This is not a valid IP value.’
| Change in operating structure |  |  | 5 | Request: The description of the slave settings button is not translated. ->Inspect after applying all translation files.
| Slave settings | Master indoor unit IP |  | 6 | 1. Symptom: When the previous button is pressed while the master indoor unit IP and extension number are set, the 'Not Applicable' information pop-up does not appear (20230919_163255.jpg) 2. Request: Modification of the Cancel button display Refer to Figma link:https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:28370&mode=design#549089050 1. Symptom: The previous button is applied on the IP setting screen. (20230919_163212.jpg) 2. Request: Request to apply by pressing the close button (also applies to other screens of the same format) Refer to figma link:https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:26286&mode=design#559650668
|  | Extension number setting |  | 7 | 1. Symptom: Slave ID has been set, but the actual IP and SUBNET are blank -> If entered manually, it operates normally, but occurs intermittently if it is not set properly. 2. Request: Bug fix
| wireless network | etc |  | 8 | 1. Symptom: A bug that causes a reboot when you press the Use Wi-Fi button in the Wi-Fi settings menu in the startup settings (however, the same function in the settings works normally) 1. Request: Fix a bug in the startup settings2. Symptom: No notification information during Wi-Fi search 2. Request: Processing information UI displayed during Wi-Fi search (refer to COMMAX UI) Refer to figma link: https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=5415:30527&mode=design#559700754 3. Symptom: When Wi-Fi is first started, the default setting is not used. 3. Request: See figma link for bug fix:https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:26288&mode=design#559698067
|  | Add network |  | 9 | 1. Symptom: Network name place holder incorrectly entered when adding (20230908_142612.jpg) 1. Request: Modified to 'Enter your Wi-Fi name' (refer to COMMAX UI) Refer to figma link:https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:26293&mode=design#559714288 | Based on the provided translation Excel document,enter your wifi name modify to enter the network name
|  | password |  | 10 | 1. Symptom: When entering the password, the default setting is not to hide characters. 1. Request: Bug fix (refer to COMMAX UI) refer to figma link:https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:26291&mode=design#559709324
|  | disconnect |  | 11 | 1. Symptom: When disconnecting, a notification pop-up is not displayed and the connection is immediately disconnected. 2. Request: Bug fix (refer to COMMAX UI)
|  | More information |  | 12 | 1. Symptoms:Security value is not displayed in detailed information 1. Request: Bug fix (refer to COMMAX UI)
| Time setting |  |  | 13 | 1. Symptom: Time value scrolling is not disabled when setting the time automatically (20230919_103216.mp4) 2. Request: Bug fix (refer to COMMAX UI)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4148:63600&mode=design#559734095
| entrance camera | Entrance camera search |  | 14 | 1. Symptom: When registering a camera, video may appear on another waiting wall pad (ID2) 1. Request: Bug fix | Not reproducible during 9/19 testing (requires reexamination later)
|  | Change default password |  | 15 |  | No inspection (default password setting required)
|  | Entrance camera preview | Entrance camera IP settings | 16 | One.Symptom : IPWhen setting Static, DHCP UIdoesn't exist (Change camera IP settings screen.jpg) 2.request :bugcorrection (COMMAX UIreference)
|  | Connection completed items |  | 17 | 1. Symptom: After connecting the front door camera, it enters sleep mode, and then when it enters again, the front door camera abnormal icon appears and does not work. 1. Request: Bug fix | not found
|  | Change entrance camera information | Name change | 18 | 1. Symptom: A character blocking button is applied to the input field where the name is entered (20230919_103846.jpg) 1. Request: Request to exclude the character blocking button from the name input field.Refer to figma link: https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:26293&mode=design#559711837 2. Symptom: When changing the name of the camera, the name does not change immediately, but changes after a while, and remains nameless for a while. 2. Request: Bug fix (name must be changed like the previous version)
|  |  | Change connection password | 19 | 1. Symptom: UI flow needs to be specified when changing password. 1. Request: Bug fix (see COMMAX UI)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4148:63600&mode=design#559755377 2. Symptom: When entering a password, the input field text for entering an existing value is 'old password' 2. Request: Modify the text 'Please enter your current password'https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4672:29404&mode=design#549114282
| Startup Settings Exit |  |  | 20 | 1. Symptom: Wording needs to be updated (indoor unit reboot message needs to be added) 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: Need to update phrase (line break, case sensitivity, add dot (.) at the end of sentence) (20230919_175438.jpg) 2. Request: Bug fix (refer to COMMAX UI)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:26281&mode=design#549119565 | 语言换行问题
home screen | Home screen Other |  |  | 21 | 1. Symptom: Need to process when there is no home screen information (visitor, call log) 1. Request: Bug fix (refer to COMMAX UI) has been applied, but line breaks in phrases in recent videos need to be processed. (20230919_105051.jpg)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4925:26255&mode=design#551622470
| mute |  |  | 22
| Preferences |  |  | 23
| hour |  |  | 24 | 1. Symptom: In English, the day of the week, month, day, and year are indicated. 1. Request: Delete ',' after the day of the week.https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4925:26255&mode=design#559788253
| Latest video |  |  | 25 | 1. Symptom: Bottom rounding of visitor video card not processed (20230919_105913.jpg) 1. Request: Bug fix (refer to COMMAX UI)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25431&mode=design#559792640
| Recent calls |  |  | 26
| entrance |  |  | 27
| call |  |  | 28
| CCTV |  |  | 29 | 1. Symptom: Restricted use icon appears on home screen even though CCTV is registered (20230919_111506.mp4) 2. Request: Bug fix
| outing |  |  | 30
| crime prevention |  |  | 31
| emergency |  |  | 32
| date time |  |  | 33
Latest video | Recent VideosOther |  |  | 34 | 1. Symptom: Door camera name is cut off in video list 1. Request: Bug fix (refer to COMMAX UI)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25433&mode=design#549972791
| Video list | still image |  | 35
|  | video |  | 36
| Check details |  |  | 37
CCTV | CCTV basic screen |  |  | 38 | 1. Symptom: CCTV IP setting UI has been implemented, but the actual change function does not work 1. Request: Bug fix 2. Symptom: When the door is called while CCTV is in operation, a problem occurs 2. Request: Bug fix 3. Symptom: CCTV operation -> Door call (multi-call) -> When changing monitoring to the door, the door screen turns off (20230919_111602.mp4) 3. Request: If a door call comes during CCTV operation, disconnect the CCTV and display the door call. CCTV does not apply multi-call rules. 4. Symptom: Even though there is one CCTV, the switch button is displayed when returning after viewing full screen (20230919_111506.mp4) 5. Request: If there is one CCTV, the switch button is not displayed.
| Screen adjustment |  |  | 39 | 1. Symptom: No screen adjustment icon 1. Request: Display of screen adjustment iconhttps://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25408&mode=design#559801604
Entrance monitoring | Monitoring basics |  |  | 40 | 1. Symptom: Switch button appears even though there is only one door camera 1. Request: Bug fix -> Button appears again after screen adjustment or volume adjustment (20230919_152728.mp4, 20230919_152706.mp4)2. Symptom: CCTV conversion button displayed during monitoring 2. Request: CCTV conversion button should not be displayed during monitoring (Refer to COMMAX UI) 3. Symptom: No voice is heard when making a call after monitoring 3. Request: Bug fix 4. Symptom: The CCTV conversion button is displayed even for numbers that do not have CCTV. 4. The CCTV conversion button is displayed only when there is a requested CCTV.5. Symptom: The mute icon is reversed (if muted, the indicator does not appear, and if not muted, the mute icon appears at the top) (20230908_195633.mp4) 5. Request: Bug fix
| Screen adjustment |  |  | 41 | 1. Symptom: CCTV button does not disappear when adjusting the screen 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: Monitoring screen adjustment value is not applied 2. Request: Apply to screen according to monitoring screen adjustment 3. Symptom: Monitoring screen adjustment value is not saved (memorized) 3. Symptom: Monitoring screen adjustment value is not saved.
| Volume control |  |  | 42 | 1. Symptom: CCTV button does not disappear when adjusting the volume 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: The default volume is set to 01. 2.Request: Must be 50
| Motion detection | When inserting an SD card |  | 43 | 1. Symptom: When you press the screen with your hand while detecting motion, the image appears momentarily. 1. Request: Make sure the flashing disappears. 2. Symptom: When you drag to select a camera item, the screen goes up, but when you release it, the camera starts again. Return to (Example: When there are 6 cameras, you try to select CCTV by dragging down, but if you let go, it goes up again and you cannot select CCTV) 2. Request: To keep the dragged camera item in the changed position so that it can be selected. Change 3. Symptom: Symptom that the information from the motion-detected camera and the alarm displayed on TUYA do not match 3. Request: Correct mobile notification information 4. Symptom: Symptom that motion cannot be detected (motion instability) 5. Request: bug fix
|  | When removing SD card |  | 44
call | call channel |  |  | 45 | 1. Symptom: Your ID is selected. 1. Request: Your ID is deactivated (refer to COMMAX UI), and the selected image of the GUI in figma is processed when pressed by hand.https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25432&mode=design#550408630 https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25432&mode=design#5504091 38
| call records | delete |  | 46 | 1. Symptom: UI Delete button does not appear after selecting item check 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: Call record delete button disappears 2. Request: Call record delete button restored to its original statehttps://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4181:16053&mode=design#559819298
| Outgoing call |  |  | 47
| Incoming call (voice) |  |  | 48 | 1. Symptom: Call destination display error (20230908_162412.jpg) 1. Request: Call destination displayed as Extection ID 1, Extension ID 2... | 已实现，但当前直接用字符串替换了，等待客户发送新的语言表格后，需更改表格
| Call connection (voice) |  |  | 49
| Call connection (video) |  |  | 50 | 1. Symptom: CCTV is set up, but the CCTV switch button is not displayed (20230919_111348.mp4) 2. Request: If CCTV is set up, the CCTV switch button is displayed (however, it only applies to call connections on the door, other video calls ( (Does not apply to security room)
| Incoming call |  |  | 51 | 1. Symptom: CCTV is set, but the CCTV switch button is not displayed. 2. Request: If CCTV is set, the CCTV switch button is displayed (however, it only applies to the call connection at the door, and does not apply to other video calls (security room). not)
| buzzer | Basic call |  | 52 | 1. Symptom: The text is not displayed in the buzzer pop-up (20230919_144549.mp4) 1. Request: Request to apply the text
|  | Busy/emergency call |  | 53 | 1. Symptom: When the buzzer rings during a door call, an instant message appears and the door call ends (20230919_145054.mp4) 1. Request: When the buzzer rings during a door call, an instant message appears, but the door call remains. Location of instant message and GUI request for changehttps://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25445&mode=design#559960911
| Door camera front door call | Incoming call |  | 54
|  | Call connection |  | 55 | 1. Symptom: Echo symptom occurs when connecting camera call 1. Request: Bug fix 2. Symptom: Abnormal door opening function - Camera 1: Entrance door opens, DDL door does not open (DDL power Bug fix 3. Symptom: The door open button is not recognized well - The door open icon stays too long when the door is opened 3. Request: Bug fix4. Symptom: After inserting the TF card and setting up video auto-save and executing a call, the product reboots. 4 Request: Bug fix -> Not reproduced when tested on 9/19 (requires recheck later)5. Symptom: When you press the door open button, talk time stops for a few seconds and all touches do not work. 6. Request: Bug fix
|  | fast mode |  | 56
|  | 2 door openings |  | 57 | 1. Symptom: Camera 2 - Door 2 does not open, When door 2 is opened, Camera 2 does not work and Door 1 opens several times 2. Request: When Door 2 is opened, Camera 2 does not work and Door 1 opens several times open
|  | Volume control |  | 58
outing | Going out settings |  |  | 59 | 1. Symptom: Even if the function is executed on the slave, the status is not shared with other devices 1. Request: Bug fix 2. Symptom: The release time for the away function is set, but it is not applied and operates immediately when the sensor is detected 2. Request: Bug fix 3. Symptom: After selecting the option to go out, visitor video is selected to be saved, but it is not saved automatically. 3. Request: Bug fix 4. Symptom: When set in the slave, no emergency occurs even if a sensor is detected 4. Request: Bug fix 5. Symptom: When calling the door camera after going out option, the master wall pad reboots. 5. Request: Bug fix 6. Symptom: Sensor set to NO cannot be selected (20230919_150436.mp4) 6. Request: All sensors can be selected, NO may be normal, and NC may be normal. If each sensor is not normal, a pop-up with information about the sensor number is displayed to encourage the user to check the sensor directly and then go out.https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4181:16053&mode=design#559845805 7. Symptom: Automatic recording does not occur in an emergency even when CCTV automatic recording is turned on. 7. Request: Setting UI is needed to implement CCTV automatic recording function.
| execution |  |  | 60 | 1. Symptom: If another emergency or call occurs during the outing operation time counter, the function is canceled 1. Request: Bug fix
| Running |  |  | 61
| end |  |  | 62 | 1. Symptom: When set on the slave, no emergency occurs even when a sensor is detected. 1. Request: Bug fix
| Emergency to go out |  |  | 63
crime prevention | Crime prevention settings |  |  | 64 | 1. Symptom: Sensor set to NO cannot be selected 1. Request: All sensors can be selected, NO may be normal, and NC may be normal. If each sensor is not normal, a pop-up with information about the sensor number is displayed to encourage the user to check the sensor directly and then go out.https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4204:27954&mode=design#559848794
| execution |  |  | 65
| Running |  |  | 66
| end |  |  | 67
| crime prevention emergency |  |  | 68 | 1. Symptom: Gradient image is not applied to the background 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: Emergency operation but no emergency sound 2. Request: Emergency sound generated -> Emergency sound generated (intermittently) There are cases where it does not occur. Recheck later) 3. Symptom: Automatic recording does not occur in an emergency even when CCTV automatic recording is turned on. 3. Request: Setting UI is needed to implement CCTV automatic recording function.
emergency | Emergency confirmation screen |  |  | 69 | 1. Symptom: Gradient image is not applied to the background 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: Emergency operation but no emergency sound 2. Request: Emergency sound generated 3. Request: Apply a single color to secure storage spacehttps://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4618:37660&mode=design#559859727 | There is enough space to store these gradient images and there is no need to make any changes
| execution |  |  | 70 | 1. Symptom: When the slave runs in an emergency, it is not immediately shared with the other device, but is shared after STOP. 2. Request: Must be shared immediately.
| Running |  |  | 71 | 1. Symptom: Emergency run sound not applied 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: Emergency run GUI guide not applied (motion, color) 2. Request: Bug fix (refer to COMMAX UI) 3. Symptom : When an emergency occurs, the date and time are not displayed (currently: 0000.00.00 00:00:00) 3. Request: When an emergency occurs, the emergency date and time are displayed. 4. Request: Apply a single color to secure storage space. Expressed by alternating two background colors.https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4181:16053&mode=design#559864231 | There is enough space to store these gradient images and there is no need to make any changes
| stop |  |  | 72 | 1. Request: Deletion of return procedure after stop is required.2. Symptom: Touching the password does not work well during emergency release. 2. Request: Change to the same as normal touch. | Screen flickering consumes a lot of memory. During the password input period, stop screen flickering alternately
| emergency records |  |  | 73 | Request: Apply crime prevention icon to emergency record restoration -> If restoration procedure is deleted, restoration item itself needs to be processed to disappear
Preferences | General (Master) | date time |  | 74 | 1. Symptom: Time value scroll is not disabled when setting the time automatically (20230919_103216.mp4) 1. Request: Bug fix (refer to COMMAX UI)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4144:38204&mode=design#559869551 2. Symptom: Even if you change the settings manually, the time is automatically updated. (Need to check: Whether the previous problem has been resolved -> RTC time becomes faster by about 3-4 seconds per day) 2. Request: Bug fix
|  | language |  | 75 | 1. Request: Place English at the top (refer to COMMAX UI)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4618:40593&mode=design#559880358
|  | password | Indoor unit password | 76 | 1. Request: Add a title to the password screen indicating what password it is (refer to COMMAX UI) https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25650&mode=design#549985430 https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25645&mode=design#5598857 022. Symptom: When changing the password on the master, it is not applied equally to the slave.
|  |  | Common entrance password | 77 | Request: No information pop-up when the common entrance is not set up (refer to COMMAX UI) ->Proceeded when working on the server system
|  | storage space | Storage space and other information | 78 | 1. Request: If there is no SD card, disable the item (refer to COMMAX UI)
|  |  | format | 79 | Symptom: Certain TF cards are not recognized by the product. Request: Improve TF compatibility.
|  |  | delete | 80 | 1. Symptom: Delete button cannot be removed from SD card 1. Request: Bug fix (refer to COMMAX UI)
|  | Door opening method |  | 81 | 1. Symptom: The set value is not loaded 1. Request: Remember the set value and display it
|  | Door opening module |  | 82
|  | Entrance camera 2 door opening number |  | 83
|  | Door camera call time |  | 84 | 1. Symptom: The call time is changed to 1, 2, and 3 minutes and runs properly, but the subtext of the setting item is displayed as 1, 3, and 5 minutes (20230908_210526.jpg)
|  | Sensor usage settings | Sensor settings when going out | 85 | 1. Request: Screen processing when there is no sensor (see COMMAX UI) 2. Symptom: Always-on sensor is also displayed (it is not displayed when actually going out, but occurs in settings) / Example: 1 when number 7 is a constant detection sensor When ~7 is used, only 6 masters are displayed, but 7 slaves are displayed. 2. Request: Bug fix
|  |  | Sensor settings for crime prevention | 86 | 1. Request: Screen processing required if there is no sensor (refer to COMMAX UI)
|  | Download mobile app |  | 87
|  | Reset user data |  | 88 | 1. Symptom: No initialization item linked to mobile app 1. Request: Bug fix (refer to COMMAX UI)2. Symptom: Even if user data is initialized, mobile app linkage remains. 2. Request: Request that mobile app linkage be disconnected when data is initialized. | Add initial user data and reboot
|  | Version information |  | 89 | 1. Symptom: No door camera version update button 1. Request: Bug fix (refer to COMMAX UI)
| Normal (slave) | language |  | 90 | 1. Request: Place English at the top (refer to COMMAX UI) https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4618:40593&mode=design#559880358
|  | storage space |  | 91
|  | Download mobile app |  | 92
|  | Version information |  | 93
| Wi-Fi | search |  | 94 | Symptom: Not all searched Wi-Fi items are displayed in the Wi-Fi section of preferences. Request: Bug fix (refer to COMMAX UI)
|  | Connection password |  | 95
|  | connected network |  | 96 | 1. Symptom: Network name place holder incorrectly entered when adding (20230908_142612.jpg) 1. Request: Modified to ‘Enter your Wi-Fi name’ (refer to COMMAX UI)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4618:41960&mode=design#559891656 | Based on the provided translation Excel document,enter your wifi name modify to enter the network name
|  | disconnect |  | 97
|  | Network information |  | 98 | 1. Symptom: Security item values of network information are not displayed 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: Wi-Fi icon appears on home screen even though there is no connected Wi-Fi (20230908_142747.mp4) 2. Request: When Wi-Fi is turned off Delete the Wi-Fi icon on the home screen 3. Symptom: After connecting Wi-Fi, it remains in the searched Wi-Fi items 3. Request: The connected Wi-Fi should not be visible in the searched WiFi items 4. Symptom: When disconnecting, a notification pop-up does not appear and is immediately canceled 4. Request : Bug fix (see COMMAX UI)
| sound | volume |  | 99 | 1. Symptom: Volume level is not adjusted 1. Request: Bug fix 2. Symptom: When adjusting the volume with the - + button, no ringtone is heard and a touch sound is made (20230908_143744.mp4) 2. Request: When adjusting the volume - + button. does not make a touch sound, and sounds a ringtone according to the sound volume adjustment. Adjust the volume in play mode (same as the scroll bar) 3. Symptom: Sound is produced even when adjusted to level 0. 3. Request: No sound is made when standing at level 0. 4. Symptom: Volume quality is deteriorated (including button sounds) 4. Request: Volume quality restoration | There is a quality issue with the ringtone and it needs to be replaced (file:/ringtone Reduce quantity. zip will be applied in the next version)
|  | Repeat indoor ringtone |  | 100 | 1. Symptom: Slave but not master (20230908_144314.mp4) (20230908_144351.mp4) 1. Request: Bug fix
|  | buzzer |  | 101 | 1. Request: Bug fix (selected sound output when selecting ringtone)
|  | household entrance |  | 102 | 1Request: Bug fix (output selected sound when selecting ringtone) 2. Symptom: Ringtone changed value is not output when calling (20230908_144440.mp4) 2. Request: Bug fix
|  | Common entrance |  | 103 | Request: Bug fix (selected sound output when selecting ringtone)
|  | security office |  | 104 | Request: Bug fix (selected sound output when selecting ringtone)
|  | extension |  | 105 | 1. Request: Bug fix (output selected sound when selecting ringtone) 2. Symptom: Ringtone setting pop-up does not appear when clicking on extension (20230908_144508.mp4) 2. Request: Bug fix
| screen | brightness |  | 106 | 1. Symptom: The minimum brightness value is too dark (20230908_144540.mp4) 1. Request: Modify to the minimum value that can be visually confirmed (minimum value 4) (20230908_145611.mp4) 2. Symptom: When the brightness is dimmed and then rebooted, the screen brightness decreases. It becomes brighter, but the value is set to the previous setting. (20230908_145845.mp4) 2. Request: Bug fix 3. Symptom: Brightness cannot be adjusted 3. Request: Bug fix
|  | Standby screen | Screen off | 107
|  |  | open frame | 108 | 1. Symptom: OpenFrame GUI guide not applied: Date time 1. Request: Bug fix (refer to COMMAX UI) 2. Symptom: Top bar is fixed and only information elements are switched 2. Request: Bug fix (refer to COMMAX UI) 3 . Requires an image to be displayed when setting a random image 3. Request: Bug fix (refer to COMMAX UI) 4. Symptom: Too dark to see in night mode 4. Request: Modify the brightness value to the minimum value that can be visually confirmed (at least 10%) ) 5. Symptom: SD card pop-up appears in recent video when displaying open frame screen (20230908_145516.mp4)(20230908_150042.mp4) 5. Request: Bug fix 6. Symptom: Background - Even if Basic is selected, the subtext appears as a random image 6. Request: Bug fix 7. Request: Delete ',' from the date notation method day of the week, month, day, and year.https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25657&mode=design#559900079
|  | Screen panel cleaning mode |  | 109
| Recording/Monitoring | Automatic recording during calls |  | 110 | 1. Request: If the SD card is not inserted when setting up automatic recording, the video item is disabled (refer to COMMAX UI) 2. Symptom: Reboot when video is selected after SD insertion (unable to check function) 2. Request: Bug fix (operation is unstable, once turned off, it continues to turn off) 3. Request: Factory default is to disable photo and video selection. , Video items are activated when an SD card is inserted. If the user inserts an SD card and removes the SD card while selecting a video, the video item is deactivated. However, when saving, the video is automatically saved as a photo. When setting motion detection, the saving method is also applied.
|  | Motion detection |  | 111 | 1. Symptom: Stability in motion detection function 1. Request: Bug fix * Refer to No. 43 2. Request: Factory default for storage format is photo, video selection is disabled, video item is activated when SD card is inserted. If the user inserts an SD card and removes the SD card while selecting a video, the video item is deactivated. However, when saving, it is automatically saved as a photo.
| Installation configuration (master) | Other inspection |  | 112 | 1. Request: Process 2 lines of installation configuration text (refer to COMMAX UI) (20230908_155630.jpg)https://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=4613:25686&mode=design#550420181 | ？I didn't notice anything different
|  | guide |  | 113
|  | Setting up the operating structure |  | 114 | 1. Request: The translation of the description of the slave setting button is not reflected. (Refer to COMMAX UI)2. Symptom: When checking after changing the slave value settings, the reboot information pop-up does not appear (20230908_151516.mp4) 2. Request: Reboot information pop-up is displayed.3. Symptom: When entering the slave ID, the IP address is not automatically entered. 3. Request: Enter the slave ID automatically.
|  | Dongho |  | 115 | 1. Request: The building number should be a 4-digit number, but any value entered can be applied in the same format. Example) 0001 input = 1 building, 001 input = 1 building, 1 input = 1 building (20230908_151758.mp4) 2. Symptoms : The value is not entered in the input field, but the Apply button does not appear. (20230908_151758.mp4) 2. Request: Apply button is displayed only when the value input/translation status in the input field changes 3. Symptom: Applied value is not saved (20230908_151758.mp4) 3. Request: Bug fix
|  | IP address |  | 116 | 1. Symptom: IP address input item is incorrect (20230908_211516.jpg) 1. Request: Input value item needs to be modified (refer to COMMAX UI) | The actual functions of the indoor unit gateway and DNS have not been implemented yet (temporarily unavailable)
|  | Operation server address |  | 117 | 1. Request: Set all defaults to 10.0.0.2
|  | Common entrance IP |  | 118 | 1. Request: Check the IP format when entering, and display a pop-up to inform you if the value is not correct (common setting items for entering IP) (20230908_152440.mp4) 2. Symptom: Applied value is not saved (20230908_152531.mp4) 2. Request : Save applied value
|  | Security office phone number |  | 119 | 1. Symptom: Displayed as IP 2. Request: Displayed as phone number (11 digits) Request application with a maximum of 11 characters (20230919_142502.mp4)2. Symptom: Applied value is not saved 2. Request: Save applied value
|  | Use of sensors |  | 120 | 1. Symptom: When moving from the sensor settings screen to the previous screen, the installation configuration information screen is displayed. 2. Request: Bug fix (refer to COMMAX UI)2. Symptom: When setting up constant detection, the value set for always detection is not displayed in the list subtext (20230908_160524.mp4) 2. Request: The value set for always detection is displayed in the list subtext (refer to COMMAX UI).
|  | Sensor test |  | 121 | 1. Symptom: Marked as checked when there is no sensor 1. Request: Bug fix (not checked if there is no sensor) (Refer to COMMAX UI) 2. Request: Displayed as a yellow icon only when the properties of the set sensor are actually detected. This is responded to by having different relative detection values depending on NO/NC.
|  | entrance camera |  | 122 | Symptom: Connection problems frequently occur after connecting the front door camera (20230908_152934.mp4) (20230908_153018.mp4) 1. Request: Bug fix 2. Symptom: Camera IP cannot be changed 2. Request: Bug fix 3. Symptom: Name When changed, the text blocking icon is displayed (20230919_103846.jpg) 3. Request: The name does not pose a security risk, so the text blocking icon is not applied.
|  | IPCCTV camera |  | 123 | 1. Symptom: When changing IP, incorrect input item title and settings title are applied. (Change camera IP settings screen.jpg)1. Request: Modification request (refer to COMMAX UI) 2. Symptom: Only one CCTV is registered (sometimes it is not registered) 2. Request: Bug fix 3. Symptom: When changing the name, a text-blocking icon appears (20230919_103846.jpg) 3. Request: The name is not a security risk, so the text is No masking icon applied
|  | Factory reset |  | 124 | 1. Symptom: Factory reset information screen does not apply 1. Request: Bug fix (refer to COMMAX UI)
| Installation configuration (slave) | Setting up the operating structure |  | 125
|  | IP address |  | 126
|  | Factory reset |  | 127
Other systems | SD card checking pop-up |  |  | 128
| SD card status notification pop-up |  |  | 129
| Formatting SD card |  |  | 130
| SD card format completed |  |  | 131
| File loading pop-up |  |  | 132
common |  |  |  | 133 | 1. Symptom: Vertical scrolling applies to the entire screen. (Startup settings, environment settings) (20230908_151615.mp4) 1. Request: Vertical scrolling applied only to elements with many items) 2. Symptom: When rebooting, the screen goes blank and reboots (once it occurs, it continues to be detected from then on) ) 2. Request: Bug fix 3. Request: Upon completion of the firmware update, request a reboot 3 seconds after the guidance message is displayedhttps://www.figma.com/file/4qhZpzGC9HyNkLmiZiTmr0?node-id=5422:39855&mode=design#559989610
CIP-D20YS |  |  |  | 134 | 1. Symptom: Recall sound does not sound when calling the front door camera 1. Request: Bug fix 2. Symptom: Factory reset button does not work 2. Request: Bug fix
TUYA mobile app |  |  |  | 135 | 1. Symptom: Symptom that TUYA video and calls are delayed too much (compared to existing 70QT or 1004QT) -> Overall, the probability of complaining about speed is very high 2. Symptom: Mobile -> Door camera: Is sound transmitted? 3. Symptom: Door camera -> Mobile: Sound is not transmitted 4. Symptom: In the mobile app, only 2 cameras and CCTV are indicated -> 6 of each should be indicated.